## Slide 1: EJ EO292 Mapping Tools & Hub Project
Emad Khatib & David Giordano DIT – PMO & Data Division EJ Council Meeting
March 26, 2024

## Slide 2: Agenda
Project Overview
Project Status, Accomplishments, and Work in Progress
Risks and Issues
Next Steps and Questions

## Slide 3: Agenda
Project Overview
Project Status, Accomplishments, and Work in Progress
Risks and Issues
Next Steps and Questions

## Slide 4: Project Overview
Project created under the direction of the Governor’s Executive Order 292
Design a Mapping Tool as a source of Environmental Justice (EJ) mapping for all North Carolinians
  Specifically, communities of color, low-income, and indigenous communities that have been disproportionately affected by climate change and environmental pollution
At a minimum, integrate data used in
  DEQ’s Community Mapping System & Environmental Justice Tool
  North Carolina Department of Health and Human Service’s Environmental Health Data Dashboard
  North Carolina Department of Transportation’s EJ and Transportation Disadvantage Index Mapping Tool

## Slide 5: Project Overview
The Mapping Tool will be used to display data related to
  Demographics
  Permitted facilities locations
  Relevant health data
  Air quality climate stressors (flooding and sea level rise risk)
  Sensitive receptors (schools, nursing homes, and affordable housing communities)
The Hub Website will be developed in coordination with DIT’s Digital Commons Team
  The Hub Website will host environmental justice information and activities as well as relevant grant information, including links to external resources
  The Hub Website will also link to the EJ Mapping Tool

## Slide 6: High-Level Governance
Development
Team
EJ EO292
Council
EJ EO292
Working Group
Proposes solutions to enable desired capabilities
Develops solution
Develops scope and approach
Oversees project execution
Presents status of project on agreed periodic basis to Council
Finalizes/approves scope and plan
Reviews/approves changes to scope/plan
Reviews/approves production deployment
Communicates status to Governor’s Office
EJ EO292
Subcommittee
Coordinate scope through direct communication with the project team
Participate in product demo/MVP
Communicates status to Governor’s Council

## Slide 7: Project Timeline

## Slide 8: Project Process

## Slide 9: Agenda
Project Overview
Project Status, Accomplishments, and Work in Progress
Risks and Issues
Next Steps and Questions

## Slide 10: Project Status
The Project Team met with DEQ, DHHS, DOT, and NCORR to review existing data layers within each of their respective applications as identified in the EO
Over 70 data layers were identified for inclusion in the EJ Mapping Tool (each layer is identified in the scoping document, along with the year it was updated, a brief description, and the data source)
Each of the required primary data layers (table on next slide) have been identified and sources documented
The Project Team has held two meetings with the Council subcommittee to provide project updates
An additional 60+ layers have been identified as data layers for consideration (identified in the scoping document)
  Demographics, environmental, health, housing/neighborhood, climate change, transportation infrastructure, compliance-facilities, equity indicators
  Layers are being reviewed for overlap with the existing data layers
  Data sources are being researched for each of the additional data layers to determine availability of authoritative data sources within NC

## Slide 11: Project Status – Required Data Layers
 | Agency |  |  |  | 
Data Element | DEQ's Environmental Justice Tool & Community Mapping System | DHHS Environmental Health Data Dashboard | DOT's EJ and Transportation Disadvantage Index Mapping Tool | NCORR Project | DMVA (TBD)
Demographic Data on Census Block Level | X | X | X | X | 
Permitted Facility Locations | X | X | N/A | N/A | 
Relevant Health Data on smallest geographic scale publicly available | X | X | X | N/A | 
Ambient air quality data | X | X | N/A | N/A | 
Climate stressors such as flooding and sea level rise risk | X | N/A | N/A | X ( General flooding, Coastal flooding, extreme heat, Landslides, and wildfires) | 
Locations of sensitive receptors such as: |  |  |  |  | 
Schools | X | X | N/A | N/A | 
Nursing Homes | X | X | N/A | N/A | 
Affordable Housing Communities | N/A | N/A | N/A | N/A | 
Grants |  |  |  |  | 

## Slide 12: Project Status – Data Mapping Update
Geographic level for each primary data layer
State
County
Census Tract
Group Block
Block
Demographic Data
Affordable Housing Communities
Ambient Air Quality Data
Relevant Health Data
Permitted Facility Locations
Climate Stressors (flooding & sea level rise)
Schools
Nursing Homes

## Slide 13: Accomplishments & Work in Progress
Recent accomplishments
  Identified data sources from each of the supporting agencies
  Data endpoints have been obtained for the supporting agency data layers
  Data layers have been identified (70+) except for DMVA
  Identified a source through OSBM that shows grant disbursement
  Identified a source through DHHS for nursing homes
  Finalized scope document
  Scope document sent to council for review and approval
Work in Progress
  Grants
    Collect links to relevant grant opportunity websites for inclusion in the hub website
    Map relevant grant disbursement information from OSBM OpenBudget site
  Affordable Housing Data
    Document the data source from Esri for Affordable Housing
  Nursing Homes
    Work with GDAC to obtain a direct feed from DHSR system
    Map data from direct feed
  Schools
    Establish a direct feed of school data from the EDDIE system
    Map data from direct feed
  Mapping Application Design
    Per the EO, collect feedback from the council on the design of the application
  Hub Website
    Continued engagement with the DIT Digital Commons team

## Slide 14: Agenda
Project Overview
Project Status, Accomplishments, and Work in Progress
Risks and Issues
Next Steps and Questions

## Slide 15
Risks |  | 
Total | Open/Monitoring | Closed
3 | 3 | 0
Confirm non-geographic view for grant opportunities; map relevant grant disbursement data Data agreement(s), if required. May not be able to secure timely. Council approvals. May not be able to secure timely. |  | 
Issues |  | 
Total | Open | Closed
5 | 4 | 1
DMVA data availability, pending inclusion Some data sources are still unknown. Need more research Council approval process | Risks are low to medium severity and currently have no impact on | 
Risks and Issues

## Slide 16: Agenda
Project Overview
Project Status, Accomplishments, and Work in Progress
Risks and Issues
Next Steps and Questions

## Slide 17: Next Steps & Questions
Identify data agreements needed, if any
Complete the work in progress items identified on previous slide
Begin the design process with input from the council
Approval Request – The project team requests approval from the Council to move forward with the next steps and data as outlined in the scoping document.
Q – The project team is now ready for input from the Council on the design of the application. How would you like to provide us with your input and guidance?
Q – How far back of historical grant data would the Council like to see mapped in the Mapping Tool? (i.e.12 months, 24 months ...etc.)?
Q – How will approval be received for project milestones in between Council regular meetings?

## Slide 18: EJ EO292 Mapping Tools & Hub Project
Emad Khatib & David Giordano DIT – PMO & Data Division EJ Council Meeting
March 26, 2024
Questions?