## Slide 1: EJ EO292 Mapping Tools & Hub Project
Emad Khatib & Matthew McLamb DIT – PMO & Data Division EJ Stakeholder Meeting
September 17, 2024

## Slide 2: Agenda
Project status
  Overall
  Feedback Status
Risks and Issues
  Public feedback
Next Steps
  MVP development
Misc.

## Slide 3: Project Status
Overall Project Status | Public participation & feedback SC | 
Area | Status – DIT | Status – Agencies
Project Management Office |  | 
Deliverable - Scope Document | Complete 3/19/24 | Complete
Council Approval | Complete 4/1/24 | 
Design – Mapping Tool | Complete | 
Hub Website Development | Complete | 
Council Approval – Design Prototype | 6/3/24 | 
Data Acquisition | Complete | 
Public Participations* | Complete | 
Council Approval – MVP Prototype | Complete | 
MVP | Pending | 
Roll Out |  | 
* Based on EJAC schedule

## Slide 4
Risks |  | 
Total | Open/Monitoring | Closed
4 | 2 | 2
Council approvals. May not be able to secure timely. Public Participation |  | 
Issues |  | 
Total | Open | Closed
9 | 0 | 9
 | Risks are low to medium severity and currently have no impact on | 
Risks and Issues

## Slide 5: Status
Work completed on the council recommendations provided by the subcommittee (See below table)
Accessibility assessment completed (layer ordering, symbology, pop-ups, layer descriptions).
EJ Hub Site introduction text complete.
Contact form – email address established (ncejac@nc.gov).
Grant intake form – details sent to DIT to add to Hub Site
Attended all public engagement meetings.
Received and reviewed feedback from the council and public. Identified 63 enhancements and addressed items (16) that have no scheduling impact, including Misty Buchanan, DNCR, comment.
Rec. Period | # of Items | Accept | Reject | Complete To-Date | In Progress
For Prototype | 24 | 23 | 1* | 23 | 
Grants | 3 | 3 |  | 3 | 
By MVP | 10 | 9 | 1** | 7 | 2
Total | 37 | 35 | 2 | 33 | 2
* Turn on/off layers with one click is not available within the application – Enhancement
** Unable to clip the NOAA data. Dropped

## Slide 6: Public Feedback – Completed Items
  Group Heat Prediction layers within one group
  Adjusted layer drawing order to ensure points are visible on top of polygons (3 comments related to this topic)
  Spelled out TDI
  Display shading at the tract level for all race categories
  Adjusted the titles for most of the health layers to ensure rate per population was included (4 public comments related to this, 34 updates made to ensure consistency)
  Added a legend for the “Community Access to Broadband Funded Locations” layer
  Moved the “Managed Conservation Areas” layer from Environmental to the Supporting Data category
  Adjusted the transparency of the polygon layers to allow you to see the road name details beneath
  Added text to the splash screen alerting users that some layers have tract level data when you zoom in
  Updated the “TDI” layer description in the “Help me understand these layers” tool to include more descriptive text

## Slide 7: Action Items - Status
  Develop the grant intake form information in the hub. In progress – DIT adding to Hub Site
  Develop the how-to video and publish to the About page
  Finalize the contact form Submit button – need email address for the Governor’s Environmental Justice Advisory Council.
  Complete the accessibility assessment (pop-ups, symbology, data layer descriptions)
  Add the introduction text to the EJ Mapping Tool and Hub Site as provided by the Governor’s Office
  Prepare for final MVP demo for council approval to roll out the HUB and Mapping tool.

## Slide 8: Next Steps
  Develop the how-to video and publish to the About page
  Grant inquiry form being added to Hub Site by DIT
  Obtain approval from the Governor’s office to lunch Hub site and Mapping tool to the public
  Launch the EJ Mapping tool and Hub
  Send enhancements list to the Governor’s Office
  Complete PTA (Privacy Threshold Analysis)

## Slide 9: Discussions/Decisions

## Slide 10: Prototype Demo – EJ Mapping Tool
 | Agency Mapping Tools |  | 
Data Element | DEQ's Environmental Justice Tool & Community Mapping System | DHHS Environmental Health Data Dashboard | DOT's EJ and Transportation Disadvantage Index mapping tool
Demographic Data on Census Block Level | X | X | X
Permitted Facility Locations | X | X | 
Relevant Health Data on smallest geographic scale publicly available | X | X | X
Ambient air quality data | X | X | 
Climate stressors such as flooding and sea level rise risk | X |  | 
Locations of sensitive receptors such as: |  |  | 
Schools | X | X | 
Nursing Homes | X | X | 
Affordable Housing Communities |  |  | 
Grants |  |  | 
Prisons & State-Owned Properties |  |  |